## Initial response GSTT
Recommendation | Current Action [any measures currently being taken to address the recommendation] | Planned Action [future actions that will be implemented to meet the recommendation] | Challenges [potential risks or difficulties and strategies to overcome them] | Priority (high/medium/low) [urgency assigned to the recommendation] | Responsible Person/Team [Name/Department] | Timeline [expected completion date]
7. Promote multilingual guidance about the move-on process and how to access health and wellbeing support after moving on from asylum accommodation. For example, by funding VCS in-reach projects and promoting Praxis A Migrant’s Guide and Groundswell ‘My rights to healthcare’ cards in asylum accommodation. | When the Refugee Asylum Seeker Service (part of the Health Inclusion Team (HIT) are made aware that a client will be moving, we direct the client to the Resettlement Team and Southwak Day Centres for Asylum Seekers (SDCAS) if they need housing support. Using telephone interpreters Clients are advised how to register with a GP and provided with written information. For clients within Core Initial Accommodation (IA) who are vulnerable or are thought to meet the priority criteria, as their GP, we provide a medical letter detailing their history and need for housing. For clients who have additional health and/or social care needs who would struggle to fully advocate for themselves, we provide an "enhanced discharge" from the service. We contact Migrant Help if they haven't registered with a GP in a timely manner, once registered, send the GP a medical summary, liaise with local services about the client's ongoing needs and, if needed, make onward referrals. For those who are at risk of becoming street homeless, or being placed in very temporoary accommdation, we suggest registering with our GP led service, the Health Inclusion Refugee Clinic in Brixton, to continue to provide primary care. We also alert the Homeless & High Intensity User (Homeless & HIU) service within the Health Inclusion Team, who offer nurse led clinics within day centres for people who are homeless. This ensures that they are aware of clients who may present, and where possible, they will complete street link referrals to connect clients to local outreach teams. | We will continue to use telephone interpreting services when sign posting to the Resettlement Team and SDCAS, providing information to support GP registration, for all. For vulnerable clients, we will continue to provide medical letters and/or enhanced discharge and suggest registeration with the Brixton Health Inclusion Clinic. Continue to work collaboratively with Homeless & HIU team. Action 1: Refugee asylum seeker service to create an accessible poster located in communal seating areas, translated into the top 5 languages, to direct Clients to SDCAS and to encourage them to notify us if they are moving, and explain how to access additional support. | The Refugee Asylum Seeker Service within HIT is not routinely informed of eviction dates, which makes it difficult to liaise with local providers regarding accommodation and health needs prior to eviction. The team must carefully balance when and how move-on support is provided, as our primary role is to support health and wellbeing. Introducing discussions about move-on too early in the asylum process may risk clients disengaging from our services. When introducing newly arrived clients to the service, we explain how the NHS works. We also ask clients to inform the Refugee Asylum Seeker Service as soon as they receive notification from the Home Office that they will be moving. In addition, we provide a standard letter explaining their entitlement to support when registering with a GP. To provide further support, a planned action is for the Refugee Asylum Seeker Service to create an accessible poster for display in communal areas. The poster will be translated into the five most commonly spoken languages and will direct clients to SDCAS, encourage them to notify us if they are moving, and explain how to access additional support. | High | Enid Grennan, Team Lead Refugee and Asylum seekers (RASS) GSTT | September 2026
11. Establish robust communication channels between housing officers and other agencies (e.g. VCS, healthcare services), providing up-to-date contact details and notification of staff changes | We have a good working relationship with agencies and teams in our area. The Refugee and Asylum Seeker Service within HIT will contact the relevant housing officer where known, or once details are provided. With consent, they will share relevant background information and identified housing needs (for example, wheelchair accessibility requirements) with the housing provider. They also work closely with the Homeless and HIU teams within HIT for people experiencing street homelessness, and with the hospital homeless team to support individuals being discharged from hospital. | Action 1: The Refugee Asylum Seeker Service will seek to explore with the Local Authority potential new pathways for information sharing and move-on planning, and how healthcare services could be involved in the process for clients identified as requiring an enhanced discharge and additional support. | Due to a combination of factors, including short timescales, high demand for housing, and challenges in sharing information across different systems, it can be difficult to ensure that clients' health and housing needs are addressed in a timely manner. This may result in clients experiencing difficulties accessing healthcare and/or being placed in accommodation that is not appropriate to their needs. The actions outlined here would seek to identify what our role could be in mitigating these challenges | High | Enid Grennan, Team Lead Refugee and Asylum seekers (RASS) GSTT | September 2025
12. Increase VCS, health services and Southwark Council teams’ participation in Southwark Private Renters’ Forum to support advocacy for refugees who are private renting or seeking private rented accommodation | We do not currently attend the Forum and have identified actions to address this recommendation. | Action 1: To contact the organiser of the Southwark Private Renters Forum, to explore what the role of the Refugee and Asylum Seeker Service could be and what we could bring to the Forum. | We do not currently work with the Forum. We would require further information about the remit and terms of reference of the forum to understand what our team or representatives role could be. To ensure that attendance is appropriate and that we can offer meaningful support. | Low | Enid Grennan, Team Lead Refugee and Asylum seekers (RASS) GSTT | September 2026
13. Align definition of key terms "vulnerability" and "priority need" used by housing teams with Shelter guidance and case law to ensure care and support needs are met under the Care Act 2014 | HIT Refuguee & Asylum Seeker Service currently aligns to statutory definitions for the key terms "vulnerability" and "priority need" . These Clients are provided with an "enhanced discharge" from the service, which includes following up on GP registration, informaiton sharing with statutory services and onward referrals. Although the Trust was not asked for a direct response, we are responding in line with the duty to cooperate and integrate services under the Care Act 2014. | Continue to advocate and support clients as required who fall into this group. To support alignment of terms the HIT refugee asylum seeker service will continue to directly reference the LA housing defintions and where needed provide the health related evidence to support; for example diagnoses, assessments of functioning and identified care needs. | As an NHS Trust, we work within statutory definitions and our duties under the Care Act, which means we’re not always able to adopt terminology used outside clinical standards and guidance. The Refugee and Asylum Seeker Service will help to address this further by exploring our role in supporting greater consistency and strengthening joint working between agencies. This could be achieved through discussions with partner agencies on a case-by-case basis, using individual Client cases to identify areas of difference, promote shared understanding, and support improved alignment of practice and decision-making. | Medium | Serina Aboim, Deputy Head of Nursing Refugee Asylum seeker service, GSTT | On-going
18. Increase provision of free legal and immigration advice, including specific advice for homeless refugees, by funding VCS delivery partners and creating a referral pathway from VCS organisations to pro bono services such as King’s College London Legal Clinic. | As an NHS service, we are unable to provide legal and immigration advice. However, we regularly sign post to VCS, predominately SDCAS, and to Migrant Help UK for support to access legal advice. Our website includes links to a range of organisations and services that provide advice. | Contine to sign post clients to voluntary sector organisations such as SDCAS and Migrant Help. Action 1: Set out a clear pathway to direct clients to the Refugee and Asylum Seeker Service Case Workers, who outreach into day centres for people who are homeless, as well as SDCAS, to provide guidance asto how to access legal advice. | Refugee and Asylum Seeker Service is not commissioned to provide legal advice. However we can and do sign post to legal services and organisations providing advice. | Low | Enid Grennan, Team Lead Refugee and Asylum seekers (RASS) GSTT | September 2026

## 6-Month Review
6 Month Performance Review - [REPORT NAME HERE] |  |  |  | PROGRESS CHARACTERISTICS • Red (R): - Indicates critical issues or delays in implementation. Criteria: - No progress or significant delays in implementing actions. - Key milestones missed without clear plans for recovery. - Recommendations with high potential harm or risk remain unresolved. • Amber (A): - Indicates moderate progress with some concerns or challenges. Criteria: - Some progress made, but not meeting established timelines. - Challenges or obstacles identified that may impact successful implementation. - Recommendations with moderate impact remain partially addressed. • Green (G): - Indicates satisfactory progress with successful implementation. Criteria: - Progress aligns with or exceeds established timelines. - Identified challenges are addressed effectively. - Recommendations with low to moderate impact are fully implemented and effective. • Not applicable (N/A): - Indicates whether the recommendation provided is applicable to the service.
ORGANISATION |  | DEPARTMENT
APPOINTED PERSON |  | REVIEWER NAME
POSITION HELD |  | REVIEWER TITLE
TODAY'S DATE |  | REVIEW DATE
RECOMMENDATION NUMBER | NOTES |  | PROGRESS
RECOMMENDATION 1
RECOMMENDATION 2
RECOMMENDATION 3
RECOMMENDATION 4
RECOMMENDATION 5
RECOMMENDATION 6
RECOMMENDATION 7
RECOMMENDATION 8
RECOMMENDATION 9
RECOMMENDATION 10
GOALS ACHIEVED WITHIN THE 6 MONTH PERIOD
NEXT STEPS IN ADVANCE OF 12 MONTH REVIEW
PARTNERSHIP WORKING New partnerships / improving collaborative working
EVIDENCING IMPACT What are the wider and longer-term benefits for service users/community/organisations involved? What can you measure or count to help show this?
ADDITIONAL COMMENTS
ORGANISATION SIGNATURE |  | REVIEWER SIGNATURE