## Initial Response
Recommendation | Current Action [any measures currently being taken to address the recommendation] | Planned Action [future actions that will be implemented to meet the recommendation] | Challenges [potential risks or difficulties and strategies to overcome them] | Priority (high/medium/low) [urgency assigned to the recommendation] | Responsible Person/Team [Name/Department] | Timeline [expected completion date]
Expand Social Prescribing Housing Officer role or fund an additional role to cover south Southwark(recommendation 4). | SEL ICB funds the borough-wide Social Prescribing model through Primary Care Networks, including link workers who routinely support people in insecure housing, asylum accommodation and move‑on settings. In Southwark, social prescribing link workers work closely with housing, advice and VCS partners to mitigate the health impacts of homelessness and housing insecurity. Social prescribing link workers work closely with housing, advice and VCS partners to mitigate the health impacts of homelessness and housing insecurity. In Southwark, social prescribing is already supporting housing-related need, including leadership from a borough lead Social Prescriber contributing to the South London Listens health and housing programme. This has included co-developing and supporting rollout of a GP resource pack to help practices respond to housing-related requests and support patients with housing applications using existing medical information At present, there is no dedicated ICB‑funded Social Prescribing Housing Officer role, nor ringfenced funding to expand an existing specialist housing post in south Southwark. The ICB is operating within a constrained personalised care and primary care budget and has prioritised sustaining core PCN social prescribing provision. | Continue to fund and sustain PCN‑based social prescribing link workers who support asylum seekers and refugees with housing‑related health issues, working alongside advice, VCS and housing partners. Through integrated commissioning forums, explore whether specialist housing expertise can be strengthened within existing social prescribing and community wellbeing models, rather than creating a new standalone post. Ensure learning from housing and migration‑focused VCS partners feeds into personalised care and neighbourhood working discussions. Build on the South London Listens health and housing approach already implemented in Southwark, including the GP resource pack and practice guidance approach by embedding the South London Listens housing guidance across primary care, strengthening the role of social prescribing link workers and care coordinators in supporting patients to navigate housing systems, complete applications and access community-based support. This supports a more integrated approach between primary care, housing and VCS partners, reducing unnecessary GP workload while improving patient experience | No dedicated ICB funding allocation exists for a specialist Social Prescribing Housing Officer role. Personalised care budgets are under pressure, limiting capacity to expand workforce roles without additional investment. Expansion is dependent on new or external funding and alignment with council‑led housing responsibilities. Delivery is reliant on existing workforce capacity and partnership working rather than a dedicated housing specialist role | Medium | Primary Care Commissioning | Ongoing
Commission a Community Embedded Worker role to provide specialised mental health support for migrants and refugees in collaboration with VCS organisations (recommendation 14). | SEL ICB is investing in community‑based mental health and wellbeing provision through VCS partners across Southwark, with commissioning principles that emphasise community embedded, culturally competent delivery. While these services support refugees and asylum seekers, there is not currently a commissioned dedicated embedded worker role focused solely on migrants and refugees. | Continue commissioning community‑based mental health and wellbeing services delivered by VCS organisations, with an expectation of inclusive access for migrants, refugees and people with insecure immigration status. Use strategic programmes such as the development of Integrated Neighbourhood Teams to promote closer partnership working between statutory services and community organisations with trusted relationships with refugee and asylum‑seeking communities. Consider the case for more specialist community‑embedded roles as part of future mental health and inequalities commissioning discussions. | There is no current funding stream for a dedicated migrant/refugee community embedded mental health worker. Mental health growth funding is fully committed to sustaining and stabilising core community mental health services. Any new specialist role would require reprioritisation or access to time‑limited funding. | Medium | Integrated Commissioning | Ongoing
Ensure the redevelopment of community mental health services explicitly addresses the needs of refugees and asylum seekers, including dedicated funding for VCS organisations supporting these groups (recommendation 15). | SEL ICB expects that community mental health services address health inequalities and improve access for underserved groups. This includes refugees and asylum seekers, who may face barriers linked to trauma, housing instability, language and immigration status, for example. As above, commissioned community mental health services are not currently solely focused on migrants and refugees. However, services including the Southwark Wellbeing Hub can and do support this population group with ongoing needs, in collaboration with relevant statutory and non-statutory organisations, particularly the voluntary sector. | Ensure that health inequalities and inclusion requirements remain central to ongoing community mental health service redesign and contract management. Continue investment in VCS‑led wellbeing and mental health support, including services that are culturally competent and accessible to refugee and asylum‑seeking communities. Link existing services providing support to asylum seekers and refugees with available open‑access prevention services, including the Southwark Wellbeing Hub, to provide earlier, non‑clinical support and navigation. | Funding for community mental health services is constrained, with limited scope for ring‑fenced investment for specific population groups. Given funding constraints, Commissioning must balance targeted inclusion with equitable access across multiple underserved communities. VCS funding is largely contractual rather than grant‑based, limiting flexibility. | Medium | Integrated Commissioning | Ongoing
Provide core, long‑term funding for VCS groups supporting migrants and refugees, including smaller organisations, and support collaboration between groups (recommendation 16). | SEL ICB supports the VCS sector through recurrent commissioning of community wellbeing and mental health services, including lead‑provider models that subcontract to smaller grassroots organisations. | Continue to commission recurrent VCS services through lead‑provider and collaborative delivery models that enable smaller grassroots organisations to participate. Through commissioning design (including the Southwark Wellbeing Hub model), encourage subcontracting, partnership working and community‑led delivery approaches. Work with local authority partners to align NHS commissioning with broader VCS funding and infrastructure support where possible. | The ICB is not currently able to provide unrestricted or core grant funding outside formal commissioning processes. Competitive procurement and contract requirements can be challenging for small organisations without support. Financial pressures across the system limit opportunities for long‑term funding expansion. | High | Integrated Commissioning | Ongoing
Commission wellbeing support for VCS groups offering services for refugees and asylum seekers (recommendation 17). | Across South East London, SEL ICB acknowledges the importance of workforce and organisational wellbeing in the VCS sector, particularly for groups supporting people with complex trauma. Some commissioned contracts include expectations around staff supervision, safeguarding support and organisational resilience. There is no standalone ICB‑commissioned wellbeing offer specifically for VCS organisations working with refugees and asylum seekers. Available funding has been prioritised towards direct service delivery rather than additional system support functions. | Embed expectations around staff support, supervision and safeguarding within commissioned VCS contracts where appropriate. Explore opportunities to support VCS workforce wellbeing indirectly through networking, partnership forums and shared learning, including links to the Southwark Wellbeing Hub and wider prevention infrastructure. Keep the wellbeing of the VCS workforce under review in future commissioning discussions (e.g. contract monitoring meetings, multi-agency governance). | There is no dedicated ICB‑commissioned wellbeing service for VCS organisations working with refugees and asylum seekers. Available funding has prioritised direct service delivery over organisational support interventions. Any future wellbeing offer would depend on additional funding and system‑wide prioritisation. | Medium | Integrated Commissioning | Ongoing

## 6-Month Review
6 Month Performance Review - [REPORT NAME HERE] |  |  |  | PROGRESS CHARACTERISTICS • Red (R): - Indicates critical issues or delays in implementation. Criteria: - No progress or significant delays in implementing actions. - Key milestones missed without clear plans for recovery. - Recommendations with high potential harm or risk remain unresolved. • Amber (A): - Indicates moderate progress with some concerns or challenges. Criteria: - Some progress made, but not meeting established timelines. - Challenges or obstacles identified that may impact successful implementation. - Recommendations with moderate impact remain partially addressed. • Green (G): - Indicates satisfactory progress with successful implementation. Criteria: - Progress aligns with or exceeds established timelines. - Identified challenges are addressed effectively. - Recommendations with low to moderate impact are fully implemented and effective. • Not applicable (N/A): - Indicates whether the recommendation provided is applicable to the service.
ORGANISATION |  | DEPARTMENT
APPOINTED PERSON |  | REVIEWER NAME
POSITION HELD |  | REVIEWER TITLE
TODAY'S DATE |  | REVIEW DATE
RECOMMENDATION NUMBER | NOTES |  | PROGRESS
RECOMMENDATION 1
RECOMMENDATION 2
RECOMMENDATION 3
RECOMMENDATION 4
RECOMMENDATION 5
RECOMMENDATION 6
RECOMMENDATION 7
RECOMMENDATION 8
RECOMMENDATION 9
RECOMMENDATION 10
GOALS ACHIEVED WITHIN THE 6 MONTH PERIOD
NEXT STEPS IN ADVANCE OF 12 MONTH REVIEW
PARTNERSHIP WORKING New partnerships / improving collaborative working
EVIDENCING IMPACT What are the wider and longer-term benefits for service users/community/organisations involved? What can you measure or count to help show this?
ADDITIONAL COMMENTS
ORGANISATION SIGNATURE |  | REVIEWER SIGNATURE