## Initial Response
Recommendation | Council department | Current Action [any measures currently being taken to address the recommendation] | Planned Action [future actions that will be implemented to meet the recommendation] | Challenges [potential risks or difficulties and strategies to overcome them] | Priority (high/medium/low) [urgency assigned to the recommendation] | Responsible Person/Team [Name/Department] | Timeline [expected completion date]
1. Influence local providers of asylum accommodation (e.g. hotels) to ensure residents' care and support needs are met. This includes provision of healthy food when residents need it and shared space for respite. | Public Health | Public Health: The Health and Wellbeing subgroup of the Borough of Sanctuary governance structure is currently working on improving the food offer and nutritional status of the residents in Home Office accommodation, based on recommendations made in the following report: https://www.sustainweb.org/reports/mar24-food-experiences-of-people-seeking-asylum-in-london/. Key action to date includes: - Close working with Environmental Health to ensure all settings have an up to date food hygiene certificate - Implementation of nutritional audits - A signposting document has been produced for all frontline staff with information on where residents can access free meals, food, vitamins and opportunities for physical activity - The nutritional standards against which the food in the accommodation is measured against has been requested from Clearsprings All hotels and other staff that work in the hotels have access to a directory of health, wellbeing and general support services for asylum seekers, refugees or migrants: https://www.southwark.gov.uk/sites/default/files/2025-12/Directory_health_wellbeing_and_support_services_for_asylum_seekers_refugees_migrants.pdf | Continue to take forward recommendations of Sustain report. | Challenges anticipated in making substantial changes to the food offer in Home Office accommodation due to national policies. Plans to work together with ADPH London to influence at a higher level. | Medium | Borough of Sanctuary Health and Wellbeing group (in relation to food actions) | Ongoing
2. Promote VCS wellbeing activities, food programmes and warm spaces in asylum accommodation. | Communications | Communications: We produce an annual mailout to all households that covers all our cost of living support, including food programmes and a map of our warm spaces. This includes to asylum accommodation. | Continue sending annual communications to asylum accommodation. | None identified | Low (already being addressed) | Communications | Ongoing
3. Empower residents in asylum accommodation and advocates (e.g. VCS groups and healthcare professionals) to report issues indicating regulatory noncompliance in asylum accommodation by providing multilingual guidance and contact information for Migrant Help. | Community Support | Community Support: The Refugee Resettlement Team supports residents and VCS partners to raise concerns about asylum accommodation via Migrant Help. Officers escalate issues relating to wellbeing, accessibility, or safety through safeguarding and partnership routes where required. | Promote consistent use of reporting mechanisms through VCS partners and outreach sessions. Reinforce messaging that reporting concerns does not impact immigration status. | Low trust in reporting systems, language barriers, and digital access limitations. | Medium | Community Support – Refugee Resettlement Team (with VCS partners) | Ongoing
5. Use reasonable adjustment flags to indicate need for an interpreter during appointments. | Public Health | Public Health: An inclusive surgeries programme was rolled out in the North Southwark GP practices in July 2025. The programme involves: - fully implementing the Doctors of the World Initiative "Safe Surgeries" which includes ensuring that interpreters are used by all practice staff when needed - appointing learning disabilities and autism champions in each practice, which will include ensuring all patients with a learning disability and / or autism who require reasonable adjustments have a reasonable adjustment plan and flag in place | Explore with the inclusive surgeries coordinator and PCN the possibility of using the reasonable adjustments flag to indicate the need for an interpreter during appointments. | None identified | Medium | Inclusive surgeries team (Public health and QHS) | November 2026
6. Gather patients feedback to evaluate the Inclusive Surgeries programme | Public Health | Public Health: A Theory of Change for the inclusive surgeries programme has been created. The Theory of Change includes the following outcomes related to patient experience which will be addressed in an evaluation: - residents and carers have improved primary care experience - enhanced trust and satisfaction in Primary Care among underserved communities - reduced stigma and discrimination experienced by underserved communities - residents have increased awareness of Primary Care services available and how to access them | An evaluation based on the theory of change is being developed. | None identified | Medium | Public Health | December 2026
7. Promote multilingual guidance about the move-on process and how to access health and wellbeing support after moving on from asylum accommodation. For example, by funding VCS in-reach projects and promoting Praxis A Migrant’s Guide and Groundswell ‘My rights to healthcare’ cards in asylum accommodation. | Community Support | Community Support: The team provide early advice and signposting to housing pathways and works with Housing Solutions, No Recourse to Public Funds (NRPF), and VCS partners to support move-on from asylum accommodation. | Strengthen early intervention at point of status grant, including clearer guidance, improved coordination with Asylum Move On Liaison Officers (AMLOs), and enhanced partnership working to support transition planning. | Short Home Office move-on timeframes, limited housing supply, and system pressure across services. | Medium | Community Support – Refugee Resettlement Team (with Housing & NRPF teams) | Ongoing
8. Commission a homelessness prevention service for single refugees, for example Bridges Outcomes Single Homeless Prevention | Housing Needs | Housing Needs: New singles pathway will be delivered through a Housing Needs reorganisation due to go live in July 2026. The aim is to provide a more structured approach to single homelessness and improving prevention outcomes for non‑priority cohorts, including refugees; supported by a dedicated Supported Lettings Team (procurement and tenancy sustainment), with further supply development through Southwark’s leadership of the Pan London Ending Homelessness Accelerator Programme (EHAP) Prevention workstream. | Develop new singles Housing Needs pathway | Increased multiple needs groups with complex needs requiring support with limited supply and increasing associated costs. | High | Housing Needs | July 2026
9. Evaluate the Refugee Rent Deposit scheme and share how learnings will be implemented. | Community Support | Community Support: The Refugee Housing Support Project, delivered by Kineara, was extended from October 2025 for one year. Client housing costs, including deposits and first months' rent, are covered by this scheme. Performance targets include using this flexible fund to enable at least 50 moves. | A formal review will be conducted after 12 months to assess outcomes and determine next steps. This evaluation will look at numbers of clients supported, housing outcomes, financial records, and qualitative feedback from clients and landlords. For further information: https://moderngov.southwark.gov.uk/ieDecisionDetails.aspx?ID=8538 | None identified | Medium | Community Support - Refugee Resettlement Team | October 2026
10. Strengthen enforcement and awareness of tenants’ rights under the Renters’ Rights Act 2025 for newly recognised refugees by providing clear information on new protections and landlord obligations and practical support including Southwark Private Renters Forum and the Private Rented Sector Ombudsman. | Community Support | Community Support: The team provides holistic support and signposting to services including housing, health, social care, and voluntary sector provision. Officers attend asylum accommodation sites to provide accessible, in-person support. | Continue strengthening multi-agency working and outreach provision to improve awareness and accessibility of services, particularly for newly arrived residents. | Fragmentation across services, language barriers, and varying awareness of entitlements. | Low | Community Support – Refugee Resettlement Team (with VCS partners) We suggest that Citizens Advice Southwark should take forward the action around strengthening awareness of Renters' Rights through the Private Renters Support Project. | Ongoing
11. Establish robust communication channels between housing officers and other agencies (e.g. VCS, healthcare services), providing up-to-date contact details and notification of staff changes. | Housing Needs; Public Health | Housing Needs: Housing Needs currently delivers prevention through eight established co‑location pathways across Health, Children’s Services, Libraries, and the Southwark Asylum Service, enabling integrated working and earlier intervention. These community‑based access points support closer coordination with partner agencies, improve information sharing, and provide residents with more accessible, joined‑up routes into housing advice and support. Public Health: In November 2025 we hosted a Health of the Borough event, on behalf of the Health and Wellbeing Board, on the topic of integrating housing and health support. This identified a number of recommendations for improving communication between Housing and other agencies, which are informing the workplan of the newly established Housing Health and Care Board and development, the 2027-2032 Joint Health and Wellbeing Strategy, and Neighbourhood Health Plans. | We will review progress against the Health of the Borough event recommendations in order to inform the work of the Housing Health and Care Board and development of the 2027-2032 Joint Health and Wellbeing Strategy. We will continue to advocate for communication between neighbourhood health and Housing services, and co-location of Housing and other community based services (an action in the current Joint Health and Wellbeing Strategy action plan 2025-2027). | Resource and staffing capacity has been noted as a challenge impacting ability to further co-locate Housing and health services (see Healthy Communities update at Health and Wellbeing Board on 12 March 2026). | Medium | Housing Needs, discharged through the Housing Health and Care Board | March 2027
12. Increase VCS, health services and Southwark Council teams’ participation in Southwark Private Renters’ Forum to support advocacy for refugees who are private renting or seeking private rented accommodation. | Public Health | Public Health: Southwark Refugees Communities Forum host a Housing Surgery for newly-recognised refugees to help them into stable accommodation, which is attended by Housing Needs (Southwark Council) and Kineara (who assist those granted the right to remain in finding accommodation in the private rented sector). This collaboration provides an avenue for the Council to support refugees with private housing issues. For reference: https://kineara.co.uk/southwark-refugee-programme/ https://www.southwarkrefugeecommunitiesforum.org/housing-surgery | No further action. | None identified | Low | N/A | N/A
13. Align definition of key terms ‘vulnerability’ and ‘priority need’ used by housing teams with Shelter guidance and case law to ensure care and support needs are met under the Care Act 2014. | Adult Social Care; Housing Needs | This recommendation is to be reviewed by Housing Needs and Adult Social Care. | Housing Needs and Adult Social Care to review this recommendation. | None identified | Medium | Housing Needs; Adult Social Care | June 2026
16. Provide core, long-term funding for VCS groups supporting migrants and refugees, including smaller organisations, and support collaboration between groups | Community Support | Community Support: Southwark has adopted a devolved grant model whereby Borough of Sanctuary funding (c.£300k) was allocated to United St Saviour’s to manage on the council’s behalf. United St Saviour’s acts as a local funder and administrator, distributing grants to VCS organisations supporting refugees and migrants. United St Saviours has also matched funding, increasing capacity in the sector. The arrangement is grant-based (not contractual), with light-touch monitoring requirements, including annual reporting on allocation, activity, and impact. This model enables flexible, multi-year funding, strengthens local VCS capacity, and supports coordinated, borough-wide delivery of services such as housing advice, legal support, and wellbeing activity. | Evaluate impacts of grant funding to inform future funding decisions. | None identified | Medium | Community Support | Ongoing
18. Increase provision of free legal and immigration advice, including specific advice for homeless refugees, by funding VCS delivery partners and creating a referral pathway from VCS organisations to pro bono services such as King’s College London Legal Clinic. | Community Support | Community Support: The council currently funds a legal immigration advice provider focused on supporting individuals within the NRPF cohort. This provision offers access to specialist immigration advice but is limited in scope to those meeting NRPF eligibility criteria. | The council will work in partnership with VCS organisations to review current legal advice arrangements and define a sustainable local approach to provision. This review will consider: - Ongoing high demand for immigration advice, particularly within the NRPF cohort - Opportunities to broaden access to advice for other groups, including newly recognised and homeless refugees - Development of clearer referral pathways, including links to pro bono services (e.g. university legal clinics) | - Sustained high demand for legal advice within the NRPF cohort - Limited capacity and funding across the advice sector - Ensuring a coordinated and equitable offer across different cohorts | High | Community Support | March 2027
19. Commission a bespoke employment service for refugees and migrants, including asylum seekers preparing to receive the right to work. For example, Refugees Better Outcomes Partnership | Community Support; Local Economy | Local Economy: Employment support is available through Southwark Works for people who have right to work, with specific providers under the Southwark Works umbrella specialising in providing support for those facing significant barriers to work, such as asylum seekers and refugees (e.g. Pecan and Connect to Work): https://southwarkworks.com/network-providers/ A referral pathway is in place between local VCS organisations acting under Southwark Works and the council's Refugee Resettlement Team. Community Support: The council does not currently have a dedicated employment service specifically for refugees and migrants. Initial scoping work has been undertaken with VCS partners, including engagement with Facework to explore potential delivery models based on their established employability programmes in other boroughs. Employment and volunteering opportunities have been identified as a key gap through engagement with partners such as the Southwark Refugee Communities Forum and Experts by Experience panel. | Community Support: The council will review options for commissioning a bespoke employment support offer for refugees and migrants as part of its wider Borough of Sanctuary approach. The review will explore how such approaches could be adapted to Southwark’s context and integrated into a sustainable, partnership-based local offer. | - Limited funding and capacity to establish and sustain a bespoke employment service - Variability in readiness to work across cohorts, including asylum seekers awaiting the right to work - Need to align employment support with wider provision (e.g. housing, ESOL, wellbeing) - Ensuring coordination across VCS partners to avoid duplication and maximise impact - Employers' understanding of right to work and eligibility - Conversion of qualifications and access to skills funding because of decision status - High level of need for ESOL with constraints in access to funding - Variable access to free childcare depending on status | High | Community Support; Local Economy | March 2027

## 6-Month Review
6 Month Performance Review - [REPORT NAME HERE] |  |  |  | PROGRESS CHARACTERISTICS • Red (R): - Indicates critical issues or delays in implementation. Criteria: - No progress or significant delays in implementing actions. - Key milestones missed without clear plans for recovery. - Recommendations with high potential harm or risk remain unresolved. • Amber (A): - Indicates moderate progress with some concerns or challenges. Criteria: - Some progress made, but not meeting established timelines. - Challenges or obstacles identified that may impact successful implementation. - Recommendations with moderate impact remain partially addressed. • Green (G): - Indicates satisfactory progress with successful implementation. Criteria: - Progress aligns with or exceeds established timelines. - Identified challenges are addressed effectively. - Recommendations with low to moderate impact are fully implemented and effective. • Not applicable (N/A): - Indicates whether the recommendation provided is applicable to the service.
ORGANISATION |  | DEPARTMENT
APPOINTED PERSON |  | REVIEWER NAME
POSITION HELD |  | REVIEWER TITLE
TODAY'S DATE |  | REVIEW DATE
RECOMMENDATION NUMBER | NOTES |  | PROGRESS
RECOMMENDATION 1
RECOMMENDATION 2
RECOMMENDATION 3
RECOMMENDATION 4
RECOMMENDATION 5
RECOMMENDATION 6
RECOMMENDATION 7
RECOMMENDATION 8
RECOMMENDATION 9
RECOMMENDATION 10
GOALS ACHIEVED WITHIN THE 6 MONTH PERIOD
NEXT STEPS IN ADVANCE OF 12 MONTH REVIEW
PARTNERSHIP WORKING New partnerships / improving collaborative working
EVIDENCING IMPACT What are the wider and longer-term benefits for service users/community/organisations involved? What can you measure or count to help show this?
ADDITIONAL COMMENTS
ORGANISATION SIGNATURE |  | REVIEWER SIGNATURE